## Slide 1
July 9, 2020

## Slide 2: Remote Meeting Instructions Phil Martinez
This meeting is being recorded.
If you want to make a comment, please raise your hand or put your comment in the chat.
Any comment in the chat will be addressed for the recording.
If you are joining via phone, you will be muted initially. During Public Comments, your phone will be unmuted and you will be able to make a comment if desired. You may also need to press “*6” to unmute your line.

## Slide 3: Agenda
Public Comments - Chair - 3 min
Approve Minutes from 5/28/20 Meeting - Chair - 2 min
Follow-Up Items:
  SharePoint Document Management Update (Informational) – Lee Wilstead – 5 min
  County-Wide Website Redesign Update (Informational) – Megan Hillyard– 5 min
  County Wide Technology FTE Map (Discussion/Direction) – Kathleen Johnston & Zach Posner– 10 min
  Case Management - JTI Support Update (Informational) – Zach Posner– 5 min
IT Lessons Learned – COVID (Informational) – Zach Posner – 10 min
Budget Update – (Informational) – Cherie Root – 5 min
Working Groups Milestone Chart (Discussion/Direction) – Zach Posner – 3 min
IT Working Group Updates
  SWG - Windows 7 Replacement Update (Informational) – Brandon Allgier - 5 min
  GWG – Business Case/Project Governance Review Process Update (Discussion/Approval) - Trevor Hebditch – 5 min
  Policy and Standards (Discussion/Approval) – Mark Evans – 15 min
    Policy 1400-7 – Payment Card Industry Data Security Standard Policy
    Policy 1400-2 – Repeal
Data Working Group Update (Informational) – Javaid Lal & Mark Evans – 10 min
Communication Items - Mayor & Council – Zach Posner & Chair – 1 min
2020 Meeting Schedule (Informational) -– 1 min
Review Action Items – Kristine Pepin - 2 min
Next Meeting – 8/13/20 – Chair - 1 min

## Slide 4: Public Comments Chair

## Slide 5: Approve Minutes Chair
Motion and Roll Call Vote

## Slide 6: Review Follow-Up Items Cherie Root
TASK | RESPONSIBLE
Windows 7 Replacement | Solution Working Group
County-Wide Technology FTE Map | IT & HR
SharePoint Document Management Update | Lee Wilstead
County-Wide Website Redesign | Megan Hillyard
Journal Technologies Incorporated (JTI) Discussion | Zach Posner
Data Working Group Update | Javaid Lal
Voting System & Equipment Update | Jerome Battle
Complete
Separate Slide
In-Process

## Slide 7: SharePoint Document Management Lee Wilstead
Libraries in Production – 18 of 70 (26%)

## Slide 8: SharePoint Document Management Lee Wilstead
Libraries in Production – 18 of 70 (26%)
Search feature deployed – March 4, 2020
    User Acceptance Testing with Treasurer / Auditor / Surveyor
Scan feature deployed – May 31, 2020
    User Acceptance Testing with Treasurer / Auditor
Custom Scan features
    Zone Scan – Developed
    Bar Code – To be developed
  Board of Equalization
    Developing workflow(s) to streamline Tax Appeal process
  Weekly Sponsor Update Meetings

## Slide 9: County-Wide Website Redesign Megan Hillyard

## Slide 10: Website Redesign Transition from Phase 1 to Phase 2
Phase 1 of the Salt Lake County Website Redesign Complete
●
●
Phase 2 Beginning Currently and Consists of 2 Parts
●
●

## Slide 11
Phase 2 Immediate Next Steps
Information Architecture
●
●
○
○
●
○

## Slide 12
Big Picture
Viable
Desirable
Feasible
Human-Centered Design:
Phase 1 Focused on the Users
Phase 2 Will Incorporate the Feasibility
and Viability Considerations for
Sustainable Website Usability

## Slide 13: County-Wide Technology FTE Map Kathleen Johnston & Zach Posner
Summary:
Total IT positions in the County – 191 (This includes merit and time limited)
Total positions in County IT – 100
Total IT positions in county agencies – 91
Job titles that IT recommends not be in the TAB report:
  Accounting Applications Manager
  Business Systems Analyst
  Fleet Systems Coordinator
  GIS Specialist
  GIS/Cadastral Supervisor
  GIS/Cadastral Tech
(These 6 jobs equate to 18 employees)
Frequency of receiving this information?
Policy around changes to technology positions? (requires a vote if yes)
Motion and Roll Call Vote
Notes: There will be a handout with detailed information (Cherie) – included in the handout sent by Kristine

## Slide 14: Case Management (Journal Technologies) (JTI) - Zach Posner - All impacted divisions are currently intending to use internal funding for maintenance for 2021 (no anticipated budget request this year). - One agency employee will be moved temporarily to IT for Case Management support.
Notes: No anticipated need this year for a budget request.

## Slide 15: IT – COVID-19 Lessons Learned Zach Posner
Self Assessment
We adapted
Customer satisfaction remained high
Need for better COOP plans
Drive to move to laptops in IT paid off
Policy
IT has an existing WFH (Work From Home) Policy
We recommend agencies adopt their own
IT will require laptops go home with staff nightly
Adopt a preference for SAAS and cloud providers via standards
Tools
Web-based collaboration tools are essential
Migrate to SAAS where possible (as part of refresh)
Pre-negotiate disaster planning with key vendors
Implement Video Suites as a standard for agency conference rooms
Morale
Maintain a sense of connectedness
Be flexible as managers, objectives vs hours
Incorporate social activities (online happy hours)
Informacast – How & When to use

## Slide 16: Budget Update Cherie Root
Business Cases are underway
If you have a 2021 budget technology request that has not been submitted, please check with your BTP ASAP to request an exception, if needed.

## Slide 17: Working Groups – Milestone Chart – Zach Posner
Notes: Q3 will be busy for the SWG and PWG groups
- SWG will be reviewing the 2021 Budget requests for technical feasibilities
- PWG will be reviewing/prioritizing the 2021 Budget requests from a County need perspective
Q4
- SWG will finalize the updated standards for the year.
- PWG will be re-evaluating the IT Governance Fund proposal (allocation for money for smaller projects)
- GWG will finalize updated Policies for the year.

## Slide 18: IT Working Group Updates

## Slide 19: Windows 7 Replacement Update – Brandon Allgier
*Counts are likely affected by COVID
Remaining Windows 7 Machines
Addressing | 2
Aging & Adult Services | 4
Animal Services | 7
Council - Tax Administration | 8
County Mayor | 1
District Attorney | 19
District Attorney - Tax Admin. | 1
Engineering & Flood Control | 3
Facilities Management | 1
Facilities Services | 20
Fleet Management | 2
Health Department | 2
Information Services | 15
Mayor Administration | 1
Mayor's Finance | 3
Parks & Recreation | 50
Printing | 1
Public Works Operations | 5
Recorder | 1
Sanitation | 4
Sheriff | 7
Solid Waste | 6
Unified Police Department | 37
Notes: Presenter – Brandon Allgier
Total is approximately 200

## Slide 20: GWG Update - Business Case Review Process – Trevor Hebditch
Notes: We have handouts for this

## Slide 21: GWG Update - IT Policy/Standards – Mark Evans
    Policy 1400-7 – Payment Card Industry Data Security Standard Policy
    Policy 1400-2 – Repeal
Notes: We have handouts for this

## Slide 22: Data Working Group Update Javaid Lal & Mark Evans
Notes: Speakers: Javaid Lal, Beth Graham, & Jeff Eason

## Slide 23
Data Coordinators Roles & Responsibilities
ROLE | NEED | TIME-COMMITMENT* | TIME-FRAME*
Act as single Point of Contact for Data Gov Working Group | Basic Understanding of agencies operations including IT, Programs, Fiscal & Personnel. | Low | As needed Attend occasional meetings
Serve as a liaison with Data Gov Working Group on issues related to data gov. | Familiarity with agency’s IT systems and databases | Low | On going Attend occasional meetings and participate in discussion regarding data gov issues
Attend trainings & workshops on data management | Basic understanding of agency IT operations. | Low | 4-6 hours (July – August) Participate in trainings & workshops to understand their roles and resources required for systems/data inventory.
Assist with System(s) inventory | Familiarity with agency’s systems and databases | Moderate | Up to 8 hours (Oct – Dec) Provide list of systems information maintained by their agency. May need to talk to system administrators and users.
Assist with database(s) inventory | Close working relations with the agency systems and database administrators. | High | Up to 40 hours (Jan 2021 – Jun 2021) Work closely with their agency systems/database administrators to provide details about the database, its content, identify classification and priorities.
Assist with implementing privacy, data licensing, metadata and other standards and practices | Be a data champion! | Low | Ongoing
Provide feedback regarding data management initiatives to Data Gov Working Group | Share best practices and ideas! | Low | Ongoing
 |  |  | *Annual – may vary based on agency size, systems and databases.

## Slide 24
Request for Data Coordinators
Update 07/08/2020
County Agency | Agency Data Coordinator | Job Title
Animal Services | Robert A.Lewis | Special Functions Manager
Criminal Justice Advisory Coun | John Krantz | Data Analyst
Criminal Justice Services | Brandi Hopkins | Data Analyst
Addressing | Teresa Curtis | Manager
Council | Shykell Ledford | Administrative and Communications Coordinator
Auditor | Brenda Nelson | Senior Internal Auditor
Mayor Financial Admin | John Pectol | Sr. Accounting Administrator
Office of Data & Innovation | Roxie McSwain | Data & Performance Analyst
Youth Services Division | Jenny Lo | Information Systems Manager
Zap Fund Administration | Jenn Waterhouse | Program Grants and Communications Coordinator
Records Management & Archives | Karri Krattley | Digital Archives Manager
Aging and Adult Services | Beth Hornbaker | Data Analyst
SLCO Arts and Culture | Mark Lawrence | D.B.A.
Recorder | Gordon Swenson | Systems Analyst
Office of Regional Development | Vikram Ravi | Data Coordinator
Facilities Services | Terry Colon | Data Analyst

## Slide 25: Work from Home Security Guidance
Data Gov Working Group and IT Security Team created an online training and “Work From Home Security Guidance.”
Targeted training for employees who are currently working from home.
The training is expected to be completed by September 30.
Number of employees who have completed the training: 501

## Slide 31: Communication Items - Mayor and Council Zach Posner & Chair
Policy 1400-7 - PCI
Policy 1400-2 – Anti-Virus (Repeal)
Voting Equipment approval

## Slide 32: Meeting Schedule For 2020 Kristine Pepin
August 13th – 10:00 a.m. – 11:30 a.m.
August 19th – Wednesday – 9:00 a.m. to 10:00 a.m.
October 22nd – 9:00 a.m. – 10:30 a.m.
December 10th – 9:00 a.m. – 10:30 a.m.

## Slide 33: Review Action Items Kristine Pepin

## Slide 34: Thank
Thank
You
You!
Next Meeting – 08/13/2020
Motion and Vote to Adjourn

## Slide 35: TO-DO List

## Slide 36: Agenda
Public Comments - Chair - 3 min (9:00 – 9:03)
Approve Minutes from 5/28/20 Meeting - Chair - 2 min (9:03 – 9:05)
Follow-Up Items:
  SharePoint Document Management Update (Informational) – Lee Wilstead – 5 min (9:05 – 9:10)
  County-Wide Website Redesign Update (Informational) – Megan Hillyard– 5 min (9:10 – 9:15)
  County Wide Technology FTE Map (Discussion/Direction) – Kathleen Johnston & Zach Posner– 10 min (9:15 -9:25)
  JTI Support Update (Informational) – Zach Posner– 5 min (9:25 – 9:30)
IT Lessons Learned – COVID (Informational) – Zach Posner – 10 min (9:30 – 9:40)
Budget Update – (Informational) – Cherie Root – 5 min (9:40 – 9:45)
Working Groups Milestone Chart (Discussion/Direction) – Zach Posner – 3 min (9:45 – 9:48)
IT Working Group Updates
  SWG - Windows 7 Replacement Update (Informational) – Brandon Allgier - 5 min (9:48 – 9:53)
  GWG – Business Case/Project Governance Review Process Update (Discussion/Approval) - Trevor Hebditch – 5 min (9:53 – 9:58)
  IT Policy and Standards (Discussion/Approval) – Mark Evans – 15 min (9:58 – 10:13)
    Policy 1400-7 – Payment Card Industry Data Security Standard Policy
    Policy 1400-2 – Repeal
Data Working Group Update (Informational) – Javaid Lal & Mark Evans – 10 min (10:13 – 10:23)
Communication Items - Mayor & Council – Zach Posner & Chair – 1 min (10:23 – 10:24)
2020 Meeting Schedule (Informational) -– 1 min (10:24 – 10:25)
Review Action Items – Kristine Pepin - 2 min (10:25 – 10:27)
Next Meeting – 8/13/20 – Chair - 1 min (10:27 – 10:28)